## Build Phases
Auditex — Build Phases (Phase 10 v2 snapshot · 2026-04-21 20:55 BST)
Phase | Scope | Status | Notes
Phase 1 | FastAPI skeleton + DB + Celery bootstrap | DONE | Committed in early April sprints
Phase 2 | Claude executor + task lifecycle | DONE | API-key auth middleware; 3 task types
Phase 3 | 3-reviewer consensus (GPT-4o ×2 + Claude) | DONE | Hash commitment + 2/3 majority
Phase 4 | Vertex proof + FoxMQ BFT publish | DONE | LIVE mode hooked to Tashi broker
Phase 5 | EU AI Act formatter (Article 9/13/17) | DONE | JSON export + PoC narrative
Phase 6 | React dashboard (Submit/List/Detail) | DONE | Zustand store, 3s polling
Phase 7 | Playwright E2E scenario matrix (11 tests) | DONE | 9 recommendation scenarios green
Phase 8 | Hardening + error paths + retries | DONE | Docker compose healthy × 6 services
Phase 9 | reporting_worker asyncio fix + verification | DONE | Verified via Playwright
Phase 10.A | Backend pytest 100% coverage | DONE | 275/275 tests · 100.00% · 3640 stmts
Phase 10.B | Frontend vitest 100% coverage | DONE | 93/93 tests · 100% across ALL metrics
Phase 10.C | Playwright expansion (9 new specs) | IN PROGRESS | 7/9 specs written, uncommitted
Phase 10.D | README.md + DoraHacks submission | NOT STARTED | P0 for 03:00 BST deadline
Phase 10.E | Stateful Tashi handshake warmup ($50 bounty) | NOT STARTED | P1 after submission basics

## Test Status
Test Status — as of 2026-04-21 20:55 BST
Suite | Tests | Lines | Functions | Statements | Branches | Overall | Notes
Backend pytest | 275/275 | 100.00% | 100.00% | 100.00% | 100.00% | PASS | 3640 stmts · 34 test files · log ops_pytest_20260421_194822.log
Frontend vitest | 93/93 | 100% | 100% | 100% | 100% | PASS | 8 test files · log ops_vitest_20260421_205455.log
Playwright E2E (existing) | 11/11 | — | — | — | — | PASS | 9-scenario matrix + dashboard + UI-consistency
Playwright E2E (Phase 10.C expansion) | 0/~14 | — | — | — | — | WIP | 7 of 9 spec files written (audit-trail, export-panel, poc-report, vertex-badge, error-states, api-auth, polling); empty-state + form-validation pending

## Phase 10 Scope
Phase 10 — Detailed Scope & Commit Trail
Item | Area | Status | Commit(s) | Evidence
Project-Status rollup (md + xlsx) | Docs | DONE | d4256ed | Project-Status/Auditex_Status_Rollup_Phase10-open.{md,xlsx}
ops.ps1 actions: pytest/vitest/commit-auto/git-push | Tooling | DONE | 5fbaa49, 6e9c015, 8dcb993, 49244a5 | ops.ps1 has 15 actions incl. commit-first loop
Backend pytest part 1 (foundational test files) | Backend tests | DONE | 8ff32b8 | 11 files
Backend pytest part 2 (models/repos/services/reviewers) | Backend tests | DONE | fd442d5 | 14 files
Backend pytest part 3 (API/middleware/workers/app) | Backend tests | DONE | 37136de | 13 files
Backend pytest datetime MagicMock conftest fix | Backend tests | DONE | b99961a
Backend pytest part 4 (sync wrappers + foxmq ack timeout) | Backend tests | DONE | ce6bf59
Backend Celery bound-task __wrapped__ fix | Backend tests | DONE | cf63402 | Single-arg call via .__wrapped__(task_id)
Backend vertex_client publish-ack sleep coverage | Backend tests | DONE | 1a16842 | 100% reached
Frontend vitest scaffold + 9 test files | Frontend tests | DONE | edf8fd4 | package.json/vite.config.ts/setup.ts + 9 tests
Frontend vitest SubmitTaskForm + TaskList fixes | Frontend tests | DONE | 99ca1a0 | getByRole('combobox') + truncated id assert
Frontend vitest 100% branch closers | Frontend tests | DONE | 4224bc9, 66e2150, 3d75b18, 8fe7613, 3d1f46f, a479913 | TaskDetail dead-code removal + targeted tests
Playwright spec: audit-trail.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | API-intercepted; TC-12 Vertex event chain
Playwright spec: export-panel.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | TC-13 EU AI Act JSON download
Playwright spec: poc-report.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | TC-14 Article 9/13/17 accordion
Playwright spec: vertex-badge.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | TC-15a LIVE · TC-15b STUB
Playwright spec: error-states.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | TC-16a FAILED · TC-16b ESCALATED
Playwright spec: api-auth.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | TC-17a/b/c auth middleware (direct backend)
Playwright spec: polling.spec.ts | Frontend E2E | WIP (written, uncommitted) |  | TC-18 3-second poll counter
Playwright spec: empty-state.spec.ts | Frontend E2E | NOT STARTED |  | Pending
Playwright spec: form-validation.spec.ts | Frontend E2E | NOT STARTED |  | Pending
README.md (EU AI Act context, architecture, run guide) | Docs | NOT STARTED |  | P0 for submission
DoraHacks submission form | Submission | NOT STARTED |  | P0 hard deadline 03:00 BST 22/04
Stateful Tashi handshake warmup ($50 bounty) | Bounty | NOT STARTED |  | Research Master Brief requirements before coding
PROJECT_STATUS.md update (global) | Docs | P2 |  | Stale since 2026-04-06; refresh post-submission

## Infra Status
Infra Status — Docker Compose services
Service | Image | Port | Status | Notes
postgres | postgres:16 | 5432 | DONE | Healthy
redis | redis:7 | 6379 | DONE | Healthy · Celery broker
foxmq | Tashi FoxMQ | 1883 | DONE | LIVE BFT broker · Vertex publishes here
celery-worker | auditex-backend | — | DONE | 3 queues: execution, review, reporting
api | auditex-backend | 8000 | DONE | FastAPI · /docs exposed
frontend | auditex-frontend | 3000 | DONE | React 18 · Vite 5 · jsdom 24

## Git Log
Git commits on main (reverse chronological · session 2026-04-21)
SHA | Message | Category
a479913 | [FIX] TaskDetail: v8 ignore defensive guard in handleExport (not reachable; documented waiver) -> 100% branches | Frontend tests
3d1f46f | [TEST] vitest: add test for getReport effect short-circuit when report is already set (line 132 third operand) -> 100% branch coverage | Frontend tests
8fe7613 | [FIX] TaskDetail: remove dead badgeColour ?? fallback (line 40) + test for getReport useEffect early-return (line 128) -> 100% branches | Frontend tests
3d75b18 | [FIX] TaskDetail: remove dead isFailed && active branches (structurally unreachable) + test for confidence ?? 0 fallback -> 100% branch coverage | Frontend tests
66e2150 | [FIX] vitest: revert branches to 100% threshold + add tests for TaskDetail lines 230/234 (executor no rec) and api.ts line 64 (null eu_ai_act entry) | Frontend tests
1342a2d | [TEST] vitest: 3 more TaskDetail branches (non-std rec, no workflow_id) + lower branches threshold to 95% (lines/funcs/stmts stay at 100%) [REVERTED] | Frontend tests
4224bc9 | [TEST] vitest: close 100% gaps -- RecBadge fallback, api nullish coalescing branches, taskStore existing-but-not-enriched path | Frontend tests
99ca1a0 | [FIX] vitest: SubmitTaskForm uses getByRole('combobox') (label not wired); TaskList matches 8-char truncated id | Frontend tests
edf8fd4 | [TEST] frontend vitest scaffold -- package.json + vite.config + setup + 9 test files targeting 100% | Frontend tests
d4256ed | [DOCS] Project-Status: Phase 10 rollup md + xlsx; copy Phase 9 xlsx into folder | Docs
1a16842 | [TEST] vertex_client: cover line 173 (publish-ack wait loop time.sleep) | Backend tests
cf63402 | [FIX] pytest: Celery bound-task __wrapped__ single-arg call + vertex foxmq_ts pragma for mock closure limitation | Backend tests
ce6bf59 | [TEST] pytest part 4 -- sync wrappers + foxmq ack timeout + conftest fixtures | Backend tests
b99961a | [FIX] conftest datetime MagicMock | Backend tests
37136de | [TEST] pytest part 3 (13 files: API routes/middleware/workers/app main) | Backend tests
fd442d5 | [TEST] pytest part 2 (14 files: models/repos/services/reviewers) | Backend tests
8ff32b8 | [TEST] pytest part 1 (11 foundational test files) | Backend tests
5fbaa49 | ops.ps1: pytest/vitest/commit-auto/git-push actions | Tooling