## Build Phases
Auditex — Build Phase Status (Phase 10 Open)
Phase | Name | Manual Test | Status | Key Commit(s) | % Done | Notes
Phase 0 | Scaffold | — | ✅ DONE | e37b9f8 | 100% | Git repo, docker-compose, run.ps1, ops.ps1, folder scaffold
Phase 1 | Database Models | — | ✅ DONE | c4dd0fb | 100% | ORM models, Alembic migration, tamper-proof audit_events (RLS+triggers)
Phase 2 | API Routes + Task Submission | MT-001/002/003 | ✅ DONE | c4dd0fb | 100% | Health, Tasks, Agents routes; X-API-Key auth; task_type + report_available in response
Phase 3 | Celery Workers + Claude Execution | MT-004 | ✅ DONE | 70023b1 | 100% | execute_task worker, claude_executor (max_tokens=2048), retry_handler, 3 task schemas
Phase 4 | Review Layer + GPT-4o + Hash Commitment | MT-005 | ✅ DONE | a5be5a9 | 100% | 3-reviewer pipeline, SHA256 hash commitment, consensus_eval (2/3 majority)
Phase 5 | Vertex Consensus Layer (stub) | MT-006 | ✅ DONE | 6585523 | 100% | Stub: real SHA-256 event hash + Redis INCR round; FINALISING status
Phase 6 | Reporting Layer + EU AI Act Export | MT-007 | ✅ DONE | bed38f1 | 100% | poc_generator, eu_act_formatter (Art 9/13/17), reports API, report_available column
Phase 7 | Dashboard Frontend (React) | MT-008 | ✅ DONE | (Phase 7) | 100% | React 18+TS+Vite+Zustand+Tailwind; 3-panel layout; live 3s polling; Playwright 11 tests
Phase 8 | Bug Fixes + Ops Improvements | — | ✅ DONE | 0309a08 / 78603b5 | 100% | reporting_worker asyncio fix; ops.ps1 Do-Git gate; claude-memory store; .gitignore restored
Phase 9 | Real FoxMQ/Vertex integration | — | ✅ DONE | 47f198f / 1cccd3c | 100% | paho-mqtt client, LIVE mode badge, STUB fallback, foxmq docker service
Phase 10.A | Backend pytest 100% coverage | — | ✅ DONE | 8ff32b8 → 1a16842 | 100% | 275 tests, 100.00% line coverage across 3640 statements; verified 19:48
Phase 10.B | Frontend Vitest unit tests | — | ❌ NOT STARTED | — | 0% | Zero Vitest today. Target: 100% component coverage. Scope: api.ts, taskStore, all components.
Phase 10.C | Playwright expansion | — | ❌ NOT STARTED | — | 55% | 11/20 covered. 9 new specs: audit-trail, export-panel, poc-report, vertex-badge, error-states, api-auth, polling, empty-state, form-validation
Phase 10.D | README + DoraHacks submission | — | 🔄 IN PROGRESS | — | 0% | P0 for deadline. Deferred per user 19:53: test coverage first, submission second.

## Test Status
Auditex — Test Status (Phase 10 Open)
Suite | Count | Result | Last Run | Notes
Backend pytest — full suite | 275 | ✅ PASS | 2026-04-21 19:48 | 100.00% coverage across 3640 statements
pytest: app.api (routes + mw) | 40 | ✅ PASS | 2026-04-21 19:48 | tasks, reports, agents, health, auth middleware
pytest: core.consensus | 32 | ✅ PASS | 2026-04-21 19:48 | foxmq_client, vertex_client, event_builder — STUB+LIVE
pytest: core.execution | 27 | ✅ PASS | 2026-04-21 19:48 | claude_executor, retry_handler, task_schemas
pytest: core.review | 36 | ✅ PASS | 2026-04-21 19:48 | coordinator, gpt4o_reviewer, consensus_eval, hash_commitment
pytest: core.reporting | 16 | ✅ PASS | 2026-04-21 19:48 | poc_generator, eu_act_formatter
pytest: db (models+repos+conn) | 40 | ✅ PASS | 2026-04-21 19:48 | task_repo, agent_repo, report_repo, event_repo, connection
pytest: services | 17 | ✅ PASS | 2026-04-21 19:48 | claude_service, openai_service — retry + error branches
pytest: workers | 29 | ✅ PASS | 2026-04-21 19:48 | execution_worker (15), reporting_worker (10), celery_app (4)
pytest: pydantic models | 14 | ✅ PASS | 2026-04-21 19:48 | TaskCreate/Response, AgentCreate/Response
pytest: app.main + config | 8 | ✅ PASS | 2026-04-21 19:48 | FastAPI app, lifespan migration paths, settings env override
pytest: conftest fixtures | 3 | ✅ PASS | 2026-04-21 19:48 | sample_executor/risk/contract_output smoke checks
pytest: db_models ORM | 9 | ✅ PASS | 2026-04-21 19:48 | TimestampMixin, UUIDPrimaryKeyMixin, repr checks
Playwright E2E — dashboard.spec.ts | 11 | ✅ PASS | 2026-04-21 15:09 | Carried from Phase 9; 3 task types × 3 recs + 2 boundaries + 1 UI
Vitest — frontend unit | 0 | ❌ NOT RUN | — | Phase 10.B — not started
Playwright — new spec expansion | 0 / 9 | ❌ NOT RUN | — | Phase 10.C — 9 proposed specs pending
BACKEND TOTAL | 275/275 @ 100% coverage

## Phase 10 Scope
Auditex — Phase 10 Open Items (Hackathon Deadline: 22/04/2026 03:00 BST)
# | Item | Priority | Status | Depends On | Notes
1 | Add ops.ps1 pytest/vitest/commit-auto/git-push actions | P0 | ✅ DONE | — | Commits 5fbaa49 / 6e9c015 / 8dcb993 / 49244a5
2 | Create GitHub repo + push backend | P0 | ✅ DONE | — | https://github.com/vsenthil7/auditex public; main tracking
3 | Backend pytest suite from zero to 100% coverage | P0 | ✅ DONE | #1 | 275 tests, 100.00% at 1a16842
4 | pytest: foundations (conftest + 10 modules) | P0 | ✅ DONE | #3 | Commit 8ff32b8 — hash_commitment, consensus_eval, schemas, foxmq, vertex, etc
5 | pytest: models/repos/services/reviewers/formatter | P0 | ✅ DONE | #3 | Commit fd442d5 — db layer, external service retry logic, gpt4o reviewer
6 | pytest: API routes + middleware + app main + workers | P0 | ✅ DONE | #3 | Commit 37136de — FastAPI routes tested via direct handler invocation
7 | pytest: conftest datetime MagicMock fix | P0 | ✅ DONE | #6 | Commit b99961a — real datetime has read-only isoformat; switch to MagicMock
8 | pytest: sync Celery wrappers + foxmq ack timeout | P0 | ✅ DONE | #3 | Commit ce6bf59 — engine dispose + loop.run_until_complete coverage
9 | pytest: Celery bound-task __wrapped__ single-arg | P0 | ✅ DONE | #8 | Commit cf63402 — bind=True means __wrapped__ is already self-bound
10 | pytest: vertex_client line 173 publish-ack sleep | P0 | ✅ DONE | #3 | Commit 1a16842 — time.time() side_effect to force one wait-loop iteration
11 | Frontend Vitest setup (100% target) | P0 | ❌ NOT STARTED | — | Add vitest + @testing-library/react + jsdom. Config with 100% threshold.
12 | Vitest: api.ts + taskStore.ts + types | P0 | ❌ NOT STARTED | #11 | Pure logic first — no DOM
13 | Vitest: StatusBadge + SubmitTaskForm | P0 | ❌ NOT STARTED | #11 | Leaf components
14 | Vitest: TaskList + TaskDetail (incl VertexModeBadge) | P0 | ❌ NOT STARTED | #11 | Mid-level composition
15 | Vitest: App.tsx + main.tsx | P0 | ❌ NOT STARTED | #11 | Root + entrypoint
16 | Playwright expansion — 9 new specs | P0 | ❌ NOT STARTED | — | audit-trail, export-panel, poc-report, vertex-badge, error-states, api-auth, polling, empty-state, form-validation
17 | README.md for submission | P0 | 🔄 IN PROGRESS | — | Deferred per user 19:53 — test coverage first. EU AI Act context + Tashi/FoxMQ story + architecture + how-to-run
18 | Check DoraHacks form requirements | P0 | ❌ NOT STARTED | — | GitHub link? Video? Slides? Verify on platform
19 | DoraHacks form submission | P0 | ❌ NOT STARTED | #17/#18 | Hard deadline 03:00 BST
20 | Project-Status rollup Phase 10 (md + xlsx) | P0 | ✅ DONE | — | This file. Created 2026-04-21 19:54.
21 | Stateful Tashi Handshake warmup ($50 bounty) | P1 | ❌ NOT STARTED | — | Deferred — after submission if time
22 | Update docs/PROJECT_STATUS.md | P2 | ❌ NOT STARTED | — | Stale at 2026-04-06. Update after submission.
23 | Session close rituals (CSRs) | P2 | ❌ NOT STARTED | — | Deferred per user: 'today last day, standardise later'

## Infra Status
Auditex — Docker + Infrastructure Status (2026-04-21 19:48)
Container | Status | Port | Health | Notes
auditex-postgres-1 | ✅ Up (healthy) | 5432 | healthy | Primary DB
auditex-redis-1 | ✅ Up (healthy) | 6379 | healthy | Broker + round counter
auditex-foxmq-1 | ✅ Up (healthy) | 1883 / 19793 | healthy | Real Tashi BFT broker (Phase 9)
auditex-celery-worker-1 | ✅ Up | — | Connected to Redis, ready | All 4 queues active
auditex-api-1 | ✅ Up | 8000 | Responding | FastAPI; runs pytest on demand
auditex-frontend-1 | ✅ Up | 3000 | Responding | React dev server

## Git Log
Auditex — Git Log (Phase 10 on top)
Commit | Phase | Message
1a16842 | 10.A | [TEST] vertex_client: cover line 173 (publish-ack wait loop time.sleep)
cf63402 | 10.A | [FIX] pytest: Celery bound-task __wrapped__ single-arg call + vertex foxmq_ts pragma
ce6bf59 | 10.A | [TEST] backend pytest part 4 -- close 100% coverage gaps (worker sync wrappers, foxmq publish-ack timeout, conftest fixtures)
b99961a | 10.A | [FIX] conftest: use MagicMock for datetime attributes so tests can override .isoformat()
37136de | 10.A | [TEST] backend pytest part 3 -- foxmq/vertex edge cases, poc_generator, auth middleware, api routes, app main, celery_app, execution_worker, reporting_worker
fd442d5 | 10.A | [TEST] backend pytest part 2 -- foxmq fix, models, db_connection, repos, services, gpt4o_reviewer, coordinator, eu_act_formatter
8ff32b8 | 10.A | [TEST] backend pytest part 1 -- conftest, config, hash_commitment, consensus_eval, task_schemas, foxmq_client, vertex_client, event_builder, claude_executor, retry_handler
49244a5 | 10 | [FIX] ops.ps1: git-push-force-upstream use plain --force not --force-with-lease
8dcb993 | 10 | [OPS] ops.ps1: add git-push-force-upstream action
6e9c015 | 10 | [OPS] ops.ps1: add git-remote-add + git-push-upstream actions
5fbaa49 | 10 | [OPS] ops.ps1: add pytest, vitest, git-push, commit-auto actions for Phase 10 test coverage push
1cccd3c | 9 | fix: execution_worker remove _STUB_MODE import -- use USE_REAL_VERTEX env var
47f198f | 9 | feat: Phase 9 -- real FoxMQ/Vertex integration; vertex LIVE/STUB badge; foxmq docker service; paho-mqtt client
c5b3fbb | 9 | docs: PHASE9-HANDOFF-PROMPT; update PROJECT_STATUS; update CLAUDE_RULES with memory backup rule
78603b5 | 8 | feat: ops.ps1 Do-Git diff+Y/N gate; claude-memory store; restore .gitignore
0309a08 | 8 | fix: reporting_worker asyncio loop bug; rename MEMORY.md to PROJECT_STATUS.md
(Phase 7) | 7 | feat: Phase 7 complete -- dashboard frontend MT-008 PASS
bed38f1 | 6 | feat: Phase 6 complete -- reporting layer EU AI Act export MT-007 PASS
6585523 | 5 | feat: Phase 5 complete -- Vertex consensus stub FINALISING status MT-006 PASS
a5be5a9 | 4 | feat: Phase 4 complete -- review pipeline GPT-4o hash commitment MT-005 PASS
70023b1 | 3 | feat: Phase 3 complete -- Celery workers Claude execution MT-004 PASS
c4dd0fb | 1/2 | feat: Phase 1+2 complete -- DB models API routes
e37b9f8 | 0 | feat: Phase 0 scaffold