## Build Phases
Auditex — Build Phase Status
Phase | Name | Manual Test | Status | Key Commit(s) | % Done | Notes
Phase 0 | Scaffold | — | ✅ DONE | e37b9f8 | 100% | Git repo, docker-compose, run.ps1, ops.ps1, folder scaffold
Phase 1 | Database Models | — | ✅ DONE | c4dd0fb | 100% | ORM models, Alembic migration, tamper-proof audit_events (RLS+triggers)
Phase 2 | API Routes + Task Submission | MT-001/002/003 | ✅ DONE | c4dd0fb | 100% | Health, Tasks, Agents routes; X-API-Key auth; task_type + report_available in response
Phase 3 | Celery Workers + Claude Execution | MT-004 | ✅ DONE | 70023b1 | 100% | execute_task worker, claude_executor (max_tokens=2048), retry_handler, 3 task schemas
Phase 4 | Review Layer + GPT-4o + Hash Commitment | MT-005 | ✅ DONE | a5be5a9 | 100% | 3-reviewer pipeline, SHA256 hash commitment, consensus_eval (2/3 majority)
Phase 5 | Vertex Consensus Layer | MT-006 | ✅ DONE | 6585523 | 100% | Stub: real SHA-256 event hash + Redis INCR round; FINALISING status added to pipeline
Phase 6 | Reporting Layer + EU AI Act Export | MT-007 | ✅ DONE | bed38f1 | 100% | poc_generator, eu_act_formatter (Art 9/13/17), reports API, report_available column
Phase 7 | Dashboard Frontend (React) | MT-008 | ✅ DONE | (Phase 7) | 100% | React 18+TS+Vite+Zustand+Tailwind; 3-panel layout; live 3s polling; 5-step view; Playwright 11 tests
Phase 8 | Bug Fixes + Ops Improvements | — | ✅ DONE | 0309a08 / 78603b5 | 100% | reporting_worker asyncio fix; ops.ps1 Do-Git gate; claude-memory store; .gitignore restored
Phase 9 | TBD — Hackathon Finalisation | TBD | 🔄 IN PROGRESS | 78603b5 | ~10% | Deadline 22/04 10:00 SGT. Scope TBD: demo polish, README, real Vertex?, submission prep

## Test Status
Auditex — Playwright Test Status (Phase 9 Open)
TC | Test Name | Last Result | Last Run | Notes
TC-01 | Dashboard loads without errors | ✅ PASS | 2026-04-21 15:09
TC-02 | document_review → APPROVE | ✅ PASS | 2026-04-21 15:09 | COMPLETED in 20s
TC-03 | document_review → NOT APPROVE (boundary: REJECT or REQUEST) | ✅ PASS | 2026-04-21 15:09 | Boundary — asserts NOT APPROVE
TC-04 | document_review → REJECT | ✅ PASS | 2026-04-21 15:09
TC-05 | risk_analysis → APPROVE | ✅ PASS | 2026-04-21 15:09 | COMPLETED in 20s; risk_level field present
TC-06 | risk_analysis → REQUEST_ADDITIONAL_INFO | ✅ PASS | 2026-04-21 15:09
TC-07 | risk_analysis → REJECT | ✅ PASS | 2026-04-21 15:09
TC-08 | contract_check → NOT REJECT (boundary: APPROVE or AMENDMENTS) | ✅ PASS | 2026-04-21 15:09 | Boundary — asserts NOT REJECT
TC-09 | contract_check → REQUEST_AMENDMENTS | ✅ PASS | 2026-04-21 15:09
TC-10 | contract_check → REJECT | ✅ PASS | 2026-04-21 15:09
TC-11 | UI consistency — all 9 tasks: 5 steps, green lifecycle, badges | ✅ PASS | 2026-04-21 15:09 | All 9 tasks checked
TOTAL | 11/11 PASSING

## Phase 9 Scope
Auditex — Phase 9 Open Items (Hackathon Deadline: 22/04/2026 10:00 SGT)
# | Item | Priority | Status | Depends On | Notes
1 | Confirm hackathon deadline + timezone on DoraHacks | P0 | 🔄 IN PROGRESS | — | Cross-project file says 22/04 10:00 SGT. Master Brief says 06/04 (outdated). VERIFY.
2 | Read Master Brief + submission requirements | P0 | 🔄 IN PROGRESS | — | doc/Hack0014-Vertex-Swarm-Challenge-Master-Brief.md — read before any build work
3 | Bring up full Docker stack (api + frontend missing) | P0 | 🔄 IN PROGRESS | Docker up | run.ps1 docker compose up -d — api and frontend containers were down at session open
4 | Demo end-to-end smoke test (manual) | P0 | ❌ NOT STARTED | #3 | Submit task → COMPLETED → View Report → Export JSON — judges will do this
5 | README for hackathon submission | P0 | ❌ NOT STARTED | — | Setup instructions, architecture overview, how to run, API key requirements
6 | Check submission form on DoraHacks — what to submit | P0 | ❌ NOT STARTED | #1 | GitHub repo link? Video demo? Slide deck? Check requirements on platform
7 | Video demo (if required) | P1 | ❌ NOT STARTED | #4 | Record walkthrough of submit → pipeline → report flow
8 | Real Vertex/FoxMQ integration (replace stubs) | P1 | ❌ NOT STARTED | — | foxmq_client.py + vertex_client.py — only needed if Tashi infra available before deadline
9 | Backend unit tests (pytest) | P2 | ❌ NOT STARTED | — | Phase 7 plan mentioned pytest backend in Phase 8 — not done. Post-hack if no time.
10 | Frontend unit tests (Vitest) | P2 | ❌ NOT STARTED | — | Phase 7 plan mentioned Vitest frontend in Phase 8 — not done. Post-hack if no time.
11 | Project-Status rollup doc + Excel | P0 | ✅ DONE | — | This file. Created 2026-04-21 15:36.

## Infra Status
Auditex — Docker + Infrastructure Status (2026-04-21 15:09)
Container | Status | Port | Health | Notes
auditex-postgres-1 | ✅ Up (healthy) | 5432 | healthy | Primary DB
auditex-redis-1 | ✅ Up (healthy) | 6379 | healthy | Broker + round counter
auditex-celery-worker-1 | ✅ Up | — | Connected to Redis, ready | All 4 queues active
auditex-api-1 | ❌ Not running | 8000 | — | Needs: run.ps1 docker compose up -d
auditex-frontend-1 | ❌ Not running | 3000 | — | Needs: run.ps1 docker compose up -d

## Git Log
Auditex — Git Log (recent)
Commit | Phase | Message
78603b5 | 8 | feat: ops.ps1 Do-Git diff+Y/N gate; claude-memory store; restore .gitignore
0309a08 | 8 | fix: reporting_worker asyncio loop bug; rename MEMORY.md to PROJECT_STATUS.md
(Phase 7) | 7 | feat: Phase 7 complete — dashboard frontend MT-008 PASS
bed38f1 | 6 | feat: Phase 6 complete — reporting layer EU AI Act export MT-007 PASS
6585523 | 5 | feat: Phase 5 complete — Vertex consensus stub FINALISING status MT-006 PASS
a5be5a9 | 4 | feat: Phase 4 complete — review pipeline GPT-4o hash commitment MT-005 PASS
70023b1 | 3 | feat: Phase 3 complete — Celery workers Claude execution MT-004 PASS
c4dd0fb | 1/2 | feat: Phase 1+2 complete — DB models API routes
e37b9f8 | 0 | feat: Phase 0 scaffold